## Changes
ID | Category | Area | Change | Detail | Status | Action needed | Files | Risk if skipped
1 | Database | Services | Provider trade name -> TIVORYX | tasks offer doc provider_name changed from 'Karan Tiwari' to 'TIVORYX' so the shop name is separate from the member name. | Applied | No | tasks/karan-house-ply-syngut-overgrip-replacement | None - already live.
2 | Database | Profile | Member name -> Karan Tiwari | users.name and stats.name changed from 'Tivoryx (Karan)' to 'Karan Tiwari'. Was NOT already that value. | Applied | No | users/FYjN50oi..., stats/FYjN50oi... | None - already live.
3 | Database | Services | uid stamped on offer docs | Links each provider offer to its owner account so Services rows can show the provider's profile photo. Pandemic Tennis has no account, so no uid. | Applied | No | 5 docs in tasks (archie, fortyforty x3, karan) | None - already live.
4 | Database | Tournament | Denormalised player-name copies fixed | event_participants.user_name and matches player/opponent name fields still read 'Tivoryx (Karan)'. Names are copied at write time, so renaming users/stats does not reach them. | Applied | No | 2 event_participants + 2 matches docs | None - already live.
5 | Database | Tournament | Zephyr Open doubles format repair | Four doubles registrations were stored in a format the UI did not count, showing 0 players. | Applied | No | scripts/fix-zephyr-doubles.mjs | None - already live.
6 | Database | Leagues | 2025 season points restored | leaguePoints25 re-added for two members (Rohan 3, Avinash 5) after confirming 2025 is a distinct season field. | Applied | No | scripts/restore-2025-season.mjs | None - already live.
7 | Database | Security | Backfill connections + public_contacts | Creates ~244 connections docs from existing accepted rallies/challenges and tournament fixtures, plus 3 marketplace seller markers. Dry-run verified; NOT run. | Pending | Run script | scripts/backfill-connections.mjs | Contact details stay readable by every signed-in member; deploying rules first would deny contact reads for everyone.
8 | Database | Security | Strip PII from users collection | Removes email/phone/whatsapp from the world-readable users collection. Dry run: 185 docs to strip, 3 skipped for having no contacts doc. NOT run. | Pending | Run script | scripts/backfill-connections.mjs --strip | HIGH - 188 members' emails and 147 phone numbers are readable by anyone on the internet, no sign-in required.
9 | Security Rules | Security | contacts read narrowed to opponents | Was 'any signed-in user'. Now owner, someone holding a connection, an organizer, or a marketplace seller with a public_contacts marker. | Not deployed | Yes | firestore.rules | Contact privacy is inert until deployed.
10 | Security Rules | Security | connections collection rules | New collection. Readable only by the two people in the pair; write: if false so only the trigger can create them. | Not deployed | Yes | firestore.rules | Contact gate cannot work without it.
11 | Security Rules | Marketplace | public_contacts collection rules | Marker saying a member has a live listing, so buyers can still contact sellers. Server-written only. | Not deployed | Yes | firestore.rules | Marketplace Contact buttons would vanish once the contacts rule ships.
12 | Security Rules | Security | pairId() must match the function | The same pair id is computed in firestore.rules and functions/connections.js. If they ever diverge, every contact read fails. | Not deployed | Yes | firestore.rules + functions/connections.js | Silent, total failure of contact reads.
13 | Cloud Functions | Security | onMatchConnection trigger | Writes a connection when a rally/challenge is accepted or a tournament fixture is created. An OPEN request earns nothing, so a number cannot be harvested by an unanswered challenge. | Not deployed | Yes | functions/connections.js | No new connections recorded; contact gate would deny everyone.
14 | Cloud Functions | Marketplace | onListingContact trigger | Maintains the public_contacts marker while a seller has at least one listing, and deletes it when their last listing goes. | Not deployed | Yes | functions/connections.js | New sellers unreachable after the rules deploy.
15 | Cloud Functions | Infra | Failed deploy diagnosed - no code change | onLadderChallengeUpdated and onZoneChangeRequested failed with AggregateError, no HTTP status, 0.8s. Transient network failure on 2 of ~10 concurrent requests; every other function in the same batch succeeded. | Informational | Retry | functions/notifications.js (unchanged) | Those two still run the previous build, so challenge-status emails are on old code.
16 | Bug Fix | Marketplace | Blank Marketplace page | lazyWithRetry returned a promise that never settled, and Suspense sat inside a route-keyed motion.main so it remounted on every navigation. Only a manual reload recovered it. | Complete | No | src/lib/lazyWithRetry.tsx, src/components/Layout.tsx, src/App.tsx | Was making the page unusable without a reload.
17 | Bug Fix | Tournament | Zone draws split in two | Pre-zone matches were keyed with no zone, so running groups showed as a category outside the zones AND every participant matched two draws, doubling the 'N signed up' count. 'No zone' now means the default zone everywhere. | Complete | No | src/pages/tournament/utils.ts, useTournament.ts | Was the reported group-view and double-count problem.
18 | Bug Fix | Tournament | Change Zone button unreachable | Gated on event.zone_draw_config?.enabled, which is null on every event, while resolveZoneConfig defaults enabled to true. The only way a player could request a zone move was invisible. | Complete | No | src/pages/Tournament.tsx | Players had no way to request a zone change.
19 | Bug Fix | Tournament | RR tile showed the wrong match | Resolved the match by isCreator first, so a creator who also plays saw an arbitrary match of that player against someone else. W/L also read from the row player's side, so your own loss showed a green W. | Complete | No | src/pages/tournament/RRGroupCard.tsx | Was reporting wrong results to the viewer.
20 | Bug Fix | Shared | Contact fetches had no per-read catch | Promise.all with no catch: one denied contacts read rejected the whole batch and blanked every contact on the page. Also a latent Object.fromEntries(null) throw. | Complete | No | src/features/leagues/useLadder.ts, src/features/friendlies/rallyService.ts | Would break every contact button the moment the contacts rule ships.
21 | Bug Fix | Tournament | Conditional React hook | useStandings was called after two early returns, so the hook count changed between renders once data arrived or the view switched. | Complete | No | src/pages/tournament/RoundRobinView.tsx | Latent crash risk.
22 | Bug Fix | Leagues | Zero-point members dropped from standings | useStandings filtered out anyone with leaguePoints26 <= 0, making every new signup invisible app-wide. | Complete | No | src/features/leagues/useStandings.ts | New members invisible on every board.
23 | Bug Fix | Marketplace | Boards stuck loading / tab out of sync | useListings never cleared loading when disabled; arriving at ?tab=rent while already mounted never opened that board. | Complete | No | src/features/marketplace/listingService.ts, src/pages/Marketplace.tsx | Board silently empty.
24 | Bug Fix | Courts | Court map zoom hid the marker | flyTo offset put the selected court 200px below centre, behind the pull-up handle, Join CTA and MapLibre attribution. | Complete | No | src/pages/CourtMap.tsx | Selected court hidden behind chrome.
25 | UI | Shared | Contact -> three icon buttons | One 'Contact' dropdown replaced by Email / SMS / WhatsApp icon buttons with the real WhatsApp mark. ~80 lines of portal, positioning and cross-instance close logic deleted. Reaches all 8 call sites including Services and Marketplace. | Complete | No | src/pages/tournament/ContactOpponentButton.tsx | -
26 | UI | Shared | Text colour swept to two tiers | 316 class changes across 56 files. text-fg for content, text-fg/70 for secondary. Dark green at 40% on a white card was unreadable in light theme. | Complete | No | 56 files | -
27 | UI | Shared | Visible borders on text fields | 18 text inputs/textareas plus the shared Input component (border-fg/10 -> /25). Deliberately excludes select dropdowns. | Complete | No | src/components/Input.tsx + 9 files | -
28 | UI | Tournament | RR group card restructured | Tiles are now MP / P-G Won (career, not group) / Contact / Score-Schedule. Organizer sees a played-pending overview instead of a Score button on other players' rows. | Complete | No | src/pages/tournament/RRGroupCard.tsx, RoundRobinView.tsx | -
29 | UI | Tournament | 'Your Group' panel removed | Duplicated what the player row now shows. The creator-only Matches list at the foot of the group card was restored in its place. | Complete | No | src/pages/Tournament.tsx, RRGroupCard.tsx | -
30 | UI | Tournament | Organizer can move players between zones | Zone picker on each player row in edit mode, reusing the existing handleMovePlayerZone. Previously reachable only for players who had filed a request. | Complete | No | src/pages/tournament/RRGroupCard.tsx, useTournament.ts | -
31 | UI | Signup | Preferences on one page | Four expandable cards (About / Skill / Courts / League), all open on arrival, each showing what you chose in its header when collapsed. | Complete | No | src/pages/Signup.tsx | -
32 | UI | Signup | Skill as tappable boxes | 7-column grid filling the card width, inset border for the selected state, band name centred beneath. | Complete | No | src/pages/Signup.tsx, ProfileInfo.tsx | -
33 | UI | Signup | Phone number tip | Signup now collects one number, so the field says which one to give: SMS/WhatsApp. | Complete | No | src/pages/Signup.tsx | -
34 | UI | Services | Add a Service form compacted | Mixed two field sizes; the shared Input (px-4 py-3, base font) replaced by the form's own compact class, matching Add an Event. | Complete | No | src/pages/services/AddServiceForm.tsx | -
35 | UI | Events | Join button beside the title | Moved out of a bordered strip at the card foot, to sit under the Edit pencil. | Complete | No | src/features/events/components/EventCard.tsx | -
36 | UI | Shared | Tree row highlight inset | The selected row's white fill ran under the parent group's label and was clipped by the card. Indent is now a left margin plus a smaller padding. | Complete | No | src/components/Tree.tsx | -
37 | UI | Profile | Favourites as pills + league quick picks | Top 3 names among men's-league members and top 3 among women's, one tap to add. Chosen names render as pills. | Complete | No | src/features/profile/favouritePlayers.ts, ProfileInfo.tsx | -
38 | UI | Profile | History tile alignment | Icon-only tile collapsed to 16px while text tiles got 28px line-height, pushing its label above the others. | Complete | No | src/pages/Profile.tsx | -
39 | UI | Profile | Quick actions moved to the top | Court and Report were below the Stats and Upcoming panels, so expanding either pushed them off screen. | Complete | No | src/pages/Profile.tsx | -
40 | UI | Shared | Player card rows | Four cells (Contact / Tags / P-G Won % / Rank Move), single-letter source tag inline with the name, vertically centred tile contents. | Complete | No | src/components/PlayerCard.tsx, Matches.tsx, Profile.tsx | -
41 | UI | Shared | Header no longer tears on scroll | Scrolled navbar became opaque instead of blurred; backdrop-filter was causing compositor paint tearing on desktop. | Complete | No | src/components/Navbar.tsx | -
42 | Documentation | Shared | CLAUDE.md: text colour rule | Two tiers only, never a dimmer one, never a theme-blind colour, disabled is opacity not a colour tier. | Complete | No | CLAUDE.md | -
43 | Documentation | Security | CLAUDE.md: contact details are opponent-only | How connections work, the pairId sync constraint, and that a denied contacts read is normal and must be caught per-read. | Complete | No | CLAUDE.md | -
44 | Documentation | Services | seed-rewards.mjs kept in step | Trade name and provider uids added so a re-seed does not undo the database fixes. | Complete | No | scripts/seed-rewards.mjs | -
45 | Cleanup | Infra | Throwaway codemod scripts removed | Five single-use scripts written to perform the sweeps (borders x3, form compaction, provider audit). | Complete | No | scratchpad only - never in the repo | -

## Summary
Change log summary
Counts are COUNTIF formulas over the Changes sheet, so they follow any row you add or edit there.
By category |  | By status |  | Needs action before it takes effect
Category | Count | Status | Count | Category | Count
Database |  | Applied |  | Database
Security Rules |  | Complete |  | Security Rules
Cloud Functions |  | Pending |  | Cloud Functions
Bug Fix |  | Not deployed |  | Bug Fix
UI |  | Informational |  | UI
Documentation |  | Total |  | Documentation
Cleanup |  |  |  | Cleanup
Total |  |  |  | Total

## Deploy Order
Deploy order - the sequence matters
Deploying the rules before the connections backfill denies contact reads for every member. Steps 1-6 are the contact-privacy chain; 7 ships the UI; 8 retries the failed functions.
Step | Command | What it does | Reversibility
1 | firebase deploy --only functions:onMatchConnection,functions:onListingContact | Trigger starts recording new connections while you work. | Safe - additive only.
2 | node scripts/backfill-connections.mjs --key serviceAccount.json --dry-run | Preview: ~244 connections + 3 seller markers. | Read-only.
3 | node scripts/backfill-connections.mjs --key serviceAccount.json | Creates the connection docs for relationships that already exist. | Additive - creates docs only.
4 | firebase deploy --only firestore:rules | Contact gate goes live. Must come AFTER step 3 or contact reads fail for everyone. | Reversible by redeploying old rules.
5 | node scripts/backfill-connections.mjs --key serviceAccount.json --strip --dry-run | Preview: 185 users docs to strip, 3 skipped. | Read-only.
6 | node scripts/backfill-connections.mjs --key serviceAccount.json --strip | Removes PII from the world-readable users collection. | DESTRUCTIVE - no backups exist. Contacts docs hold the only other copy.
7 | firebase deploy --only hosting | Ships every UI and bug fix in this log. | Reversible by redeploying.
8 | npx firebase deploy --only functions:onLadderChallengeUpdated,functions:onZoneChangeRequested | Retry of the two that hit a network error. | Safe - retry of a failed deploy.

## Open Items
Category | Area | Item | Why it is open | Suggested action
Security | Events | useJoin.ts reads zone_draw_config raw | Same bug class as the Change Zone button: the field is null on every event, so the 'late joiners may only take a slot in their own zone' restriction never applies. | Decide whether to enforce it - fixing changes who can join which bracket.
Database | Services | Legacy inactive Karan offer doc | active:false, old stringer_id/stringer_name shape, no category. Filtered out of the catalog so it never renders. | Delete if you want the collection clean.
Cleanup | Infra | scripts/fix-offer-providers.cjs | Dated Aug 10, predates this session, not mine. Overlaps with the provider uid + TIVORYX work now applied. | Review and delete if redundant.
Cleanup | Tournament | Unused props after 'Your Group' removal | isParticipant on RRGroupCard, userRRGroup and userRRMatches in Tournament.tsx. tsc does not flag them. | Remove if you want them gone - needs edits up the prop chain.
UI | Shared | placeholder-gray-500 is theme-blind | Hardcoded grey on inputs across the app, which the new CLAUDE.md text-colour rule forbids. | Separate sweep.
Security | Infra | Rules deploy state unverified | A speculative 'firebase deploy --dry-run' was started and killed mid-run; whether it released a ruleset was never confirmed. | Check Firebase Console > Firestore > Rules history before deploying.

## Legend
How to use this workbook
Changes | The full log. Row 1 has filter arrows - click Category, Area or Status to narrow it.
Status: Applied | Written to production already. Nothing further to do.
Status: Complete | Code change made and type-checked; ships with the next hosting deploy.
Status: Pending | A script exists but has NOT been run.
Status: Not deployed | Code or rules written but not pushed to Firebase.
Status: Informational | Diagnosis or context, no change required.
Deploy Order | Run top to bottom. Order is not cosmetic - see the note on that sheet.
Open Items | Known issues deliberately not addressed, with a suggested action for each.
Verification | Every code change passed tsc --noEmit. There are no automated tests in this repo, and per CLAUDE.md no dev server was started - UI changes need your eye.
Source | Compiled from the working-tree changes of the 11-12 Aug 2026 session. Document counts (244 connections, 185 users to strip) come from dry runs against production.