## Bug Reports
ID | Change description | Type | What was done | Improvement / new behaviour
BUG-001 | Court Map search box: a border was drawn around the inner text field, inside the already-rounded search pill, so the control looked like a box within a box. The container's focus-within style was dead because the container itself carried no border. | UI/UX | Removed `border border-fg/25` from the search <input> in src/pages/CourtMap.tsx. Confirmed against git history that the input was borderless before commit 11ce4c8, where a sweep moved the border off the outer pill and onto the inner field. | The search bar is a clean borderless pill, matching the borderless filter controls elsewhere on the map. Background and focus ring carry the affordance instead.
BUG-002 | Submitting a score on a Friendly did not record the match — it proposed converting the Friendly into a Challenge. The one-tap confirm for that proposal was dead code nothing called, so the opponent instead got a generic Accept and then had to re-enter the same score on the Challenges tab before anything counted. Friendlies were effectively worth nothing unless both players did the work twice. | Behaviour change | A Friendly score now reports against its own rally doc (reportRally) instead of calling proposeConversion; the dead confirmConversion was deleted. A second party — the other player, or an admin — confirms via resolveRally. New Cloud Function functions/friendlyPoints.js pays the points on that confirm, in a transaction stamped `applied` so a double-tap pays once. New firestore.rules clauses allow rally report + confirm; the confirmer can never be reported_by, which is what stops a player self-awarding points. Score modal title 'Friendly -> Challenge' changed to 'Record Match'. Tab blurb changed to 'Submit the score to record a friendly match, both players get points.' Stepper (+/-) now also accepts a typed number, digits-only and clamped. Added the set-integer validation the friendly path previously lacked. NOTE: needs `firebase deploy --only firestore:rules` and `--only functions` before the client goes live, or every Submit is denied. | A Friendly is recorded as a real match once a second party confirms it. Winner +2 and loser +1 leaguePoints26 — a friendly never costs points, unlike a Challenge's +/-3. Both players also get matchesPlayed +1 and a win/loss. Points are written server-side only, and exactly once.
BUG-003 | Contact buttons spilled out of their card on smaller screens. The control is up to three no-wrap icon pills forming a rigid ~90px block with no wrapping and no ability to shrink, while several containers give it far less room — the round-robin group card allots it one cell of a 4-column grid, about 58px on a 320px phone. | UI/UX | ContactOpponentButton's wrapper given flex-wrap and min-w-0 so the pills can wrap and the control can shrink. RRGroupCard's stat tiles given min-w-0 so a 4-column track can actually shrink. OpponentPanels' right column given min-w-0, and its 'Scheduled on <date>' badge capped with max-w and truncate — untruncated, it set the column's width and forced the whole row wider than the viewport. | Contact buttons wrap inside their cell instead of spilling into neighbouring columns, and rows are no longer forced wider than a 320px screen. Low-risk call sites (marketplace, services) were left alone — their siblings already truncate.
BUG-004 | No way for an organizer to award a round-robin group's bonus points. The +5 group bonus was paid automatically the moment the last match in a group was confirmed, with no organizer involvement and no visible signal to anyone that it had happened — players could not tell whether their group had been paid, and an organizer had no way to pay a group that the automatic commit had missed (it ran as a separate best-effort batch that could fail while the scores landed). | UI/UX | Added a 'Group Bonus' switch to the header of every round-robin group card (src/pages/tournament/RRGroupCard.tsx) — the same toggle control the profile card uses for Email Notifications. Visible to everyone; only the event creator/organizer can move it. Players see it disabled, with no 'organizer only' label. The label reads 'Group Bonus' before and 'Bonus Awarded' after. New handleSetGroupBonus in useTournament.ts: creator-gated and two-way — on pays every player in the group, off takes the same amount back. Both directions confirm first, and the award confirm warns if the group still has unplayed matches. rr_group_bonus_v2 on the group's match docs is the switch's stored state, so every viewer reads the same position off the live feed and a repeat write in the same direction no-ops. Removed the automatic payout from updateMatchWithSubmission — the switch is now the only way the bonus ever moves. The amount is a single RR_GROUP_BONUS constant shared by the payout and reverseRRBonusesInto, so the two can't drift. reverseRRBonusesInto no longer requires the group to be fully played before deducting — the organizer may now award an incomplete group, and the stamp is the only proof of payment. Switch is hidden before the draw is generated (no match docs to pay or stamp). | The organizer decides when a group's bonus is paid, can pay a group the old automatic commit missed, and can undo a mis-press instead of being stuck with it. Both organizer and players can see at a glance whether a group has been paid — 'Group Bonus' before, 'Bonus Awarded' after. A draw reset still reverses exactly what was paid, and nothing else.
BUG-005 | Court Map filters were inconsistent and under-powered. (a) Type options were bare and ambiguous ('Public', 'Club', 'Open Hours') with no way to ask for tennis or pickleball directly. (b) Pickleball-only sites appeared only when Type was completely empty AND the 'All Courts' layer toggle was on, so no combination of controls reliably showed them. (c) Zone and Total Courts were single-select, so 'two neighbouring zones' or 'under 4 or more than 8 courts' took two searches. (d) The panel showed a different set of controls depending on whether the results list happened to be showing courts or programs. | UI/UX + behaviour change | Type reworked to eight options: All, Tennis, Pickleball, Public Tennis Courts, Tennis Clubs, Tennis Programs, Court Bookings, Clubs with Public Hours. 'Clubs with Public Hours' now also requires courtType == club, matching its new name. Deleted PROGRAM_TYPE_OPTIONS, a byte-identical duplicate. Pickleball sites now show under All and Pickleball only — every other type is a tennis-court filter. Selecting Pickleball also overrides the 'members only' default view, because these sites carry no check-in counts and would otherwise always return empty. Zone and Total Courts became multi-select via a new MultiFilterSelect control (a checklist popover modelled on the old DaysDropdown, borderless to match FilterSelect). Selections inside one filter OR together; the filters still AND. Type and Lights stay single-select — Lights is Yes/No, where picking both just means All. One filter view in every state: Type, Lights, Zone, Total Courts. The separate programs filter panel was removed — see BUG-006. | The Type filter names what it actually filters and reaches tennis or pickleball in one selection; pickleball is visible under All and Pickleball and hidden under every tennis-only type; Zone and Total Courts take any number of values; and opening the filters always gives the same four controls.
BUG-006 | Tennis programs were badly served throughout. (a) 'Tennis Programs' sat in the Type filter but was not a filter — it replaced the whole page, swapping the court list for a program list and the four court filters for Status/Age/Days, and there was no way to see which courts run programs. (b) Program rows showed only the park name, so a location running several sessions produced a screen of identical rows — four consecutive 'Trinity Bellwoods Park / Jun 29 – Aug 24 / ONGOING' entries with nothing to tell them apart, though the title, schedule and age range were all parsed and available. (c) Programs were sorted oldest-first, so finished sessions filled the top and the ones you could still join were buried — in May a player saw last winter's before June's. (d) The Status filter was two taps away in the filter sheet, had no 'Past' option, and used a second inline implementation that could disagree with the badge on each row. (e) 'View Activity' was a plain text link with a small tap target. | UI/UX + behaviour change | 'Tennis Programs' is now a real filter (courts that run programs), leaving you in the court list. The programs list became a drill-down from one court; isPrograms derives from progLocationFilter rather than the Type value. 'View Available Programs' opens that list in the results panel and now also sets mobileResultsOpen — on mobile the panel is collapsed by default, so the tap had looked inert. There is deliberately no back control: Reset in the filter sheet returns you to the courts. Program rows now lead with the program's title, then location, time range, date range, then status, days and age as pills. Falls back to the location name when a program has no title. Ordering is Upcoming, then Ongoing, then Past — soonest-first within the first two, newest-first within Past. A typed address still sorts purely by distance, unchanged. Status became four pills (All / Upcoming / Ongoing / Past) on the 'Showing X of Y programs' line, with the missing Past option added, now calling the same getProgramStatus helper the row badge uses — the old inline version had no 'past' branch and silently matched every program. 'View Activity' is a filled clay pill button (still an anchor — it opens the City of Toronto page in a new tab); the trailing arrow was dropped since the button shape signals the action. The Age and Days filters, their state, PROGRAM_AGE_OPTIONS and the now-unused DaysDropdown component were all removed. | Every entry in the Type filter filters courts. Each program session is identifiable at a glance — which program, what time, which days, what ages — the ones you can still join lead the list, status filtering is one tap and always agrees with the row badges, and the row's action is obviously tappable.
BUG-007 | A court's Book Online and View Available Programs actions existed only inside the map popup, so from the results list you had to first find and tap the court's marker to reach them. | UI/UX | Court result rows now carry 'Book Online' and 'Programs' buttons beneath the distance, right-aligned, shown only when the court has a booking URL or runs programs. The row had to stop being one large <button> to hold them — nesting a button or link inside a button is invalid HTML and swallows the inner control's clicks. The row is now a div, with the court-selecting area still a button beside the new action column. | Booking and programs are reachable straight from the list without going via the map marker, and the row's main tap still opens the court.
BUG-008 | Knockout late joiners silently never reached the draw, and the organizer had no way to see it. On joining, the client checks for an open slot and then tries to write the player into it — but that write is organizer-only under firestore.rules, so for an ordinary player it is denied, caught, and logged to console in their own browser. The registration succeeds; the seating does not. There is no knockout equivalent of the round-robin auto-placer, and the only unplaced-player list in the app (rrUnplacedPlayers) returns empty whenever there are no RR group matches — i.e. always, on a knockout event. Found live on Zephyr Open 2026 Singles: 14 of 46 registered players were in no match at all, with joins spanning three weeks. | UI/UX | New organizer-only 'Unplaced players' dropdown on the Tournament page, shown once a draw exists (before that, 'unplaced' is everyone and says nothing). New unplacedParticipants in useTournament.ts: everyone registered for the event, not removed, whose uid appears in no match of the event. Scoped event-wide rather than per-draw so nobody is hidden. New openDrawSlots: free slots in the current draw. BYE slots are deliberately NOT offered — a BYE's opponent has already been advanced past it, so filling one desyncs the next round. New handleSeatParticipant writes the name and uid into the chosen slot, re-checking the slot is still free first. Each row shows the player's format, division and skill so the organizer can tell which draw they belong in; a note appears when the current draw has no free slots. | The organizer can see who registered but never made it into a draw, and place them in two taps instead of it being invisible.
BUG-009 | Organizer request queues were always-open amber panels stacked down the page, and the schedule-request queue only ever showed the tournament currently on screen — so an organizer running several tournaments had to visit each one to find pending requests. | UI/UX | Schedule requests now span every tournament the signed-in organizer created, which is why each row carries its tournament name beneath the pairing. Implemented as one single-field onSnapshot on schedule_requested (no composite index required; matches are readable by any signed-in user, so no rules change), filtered client-side to events whose creator_id is the current user. A failed read empties the queue rather than stranding a stale list. New shared QueueDropdown component collapses each organizer queue behind a header with a count, so they read as a stack of dropdowns rather than a column of open panels. Both new dropdowns reuse the app's existing controls — the same select, Button and chevron patterns used elsewhere on the page. Groundwork for the planned organizer-overview view, which these queues will move behind. | One place to see and action scheduling across all of an organizer's tournaments, and a shorter page: queues are collapsed until opened.
BUG-010 | A group match had only two possible outcomes, and both demanded a winner: a played result, or a walkover — which pays the same 3 points to the winner and 1 to the loser. An organizer had no way to close out a group match that simply never happened. Leaving it unplayed keeps the group open indefinitely (and blocks the Group Bonus), while recording it as a walkover forces them to name a winner and hands that player 3 points for a match nobody turned up to. | Improvement | New third outcome: 'Count As No Show', a checkbox beside 'Also count as a Challenge' in the score modal. Visible only to the event creator/organizer, and only on round-robin group matches — a no show has no winner, so in a knockout there would be nobody to advance. Awards NO_SHOW_POINTS (1) to BOTH players. No winner, no games, and deliberately no matchesPlayed, win or loss — a match nobody played must not dilute either player's win rate. The match still goes to 'complete' so the group can finish and the Group Bonus becomes available. Ticking it disables the winner cards, the set steppers and the Challenge checkbox, and the submit button becomes 'Record No Show'. COLLISION HANDLED: an all-zero score already meant 'walkover', and a no show is also all-zero. no_show is therefore tested BEFORE the walkover check, before the blank-winner_uid guard (which it is the one legitimate exception to), and first in reverseMatchStatsInto — which previously returned early on a missing winner_uid, so a draw reset would have left both players holding a point from a deleted match. computeGroupStandings in rrGeneration.ts got the matching branch, since the two scoring implementations have to stay in step. The organizer-only and RR-group-only rules are re-checked in handleSubmitScore, not just enforced by hiding the checkbox. Display: the group card would have shown a red 'L' to BOTH players (no winner means nobody matches the win test) — the W/L pill is now suppressed and rows read 'No show' and 'No show · 1 pt each'. Ticking No Show after already picking a winner no longer fires a challenge conversion for that winner. The three-outcome rule and its ordering constraint were added to CLAUDE.md. The two score-modal options now sit on ONE line rather than stacked: flex-wrap so the second drops below only when the sheet is genuinely too narrow, min-w-0 so each label's own text wraps instead of forcing the row wider than the modal, and items-start so the checkbox aligns to the first line of a wrapped label. | An organizer can close out a group match nobody played, in one tick, without inventing a winner. Both players get 1 point, the group can complete, and neither player's win percentage is touched. Reversal on a draw reset takes back exactly what was paid.
BUG-011 | There was no way to undo a single match's score. The only reset in the tournament was 'Cancel Matches' at draw level, which deletes EVERY match in the draw and reverses every completed match's stats — so correcting one wrongly-entered result meant either destroying the whole draw or living with it. Re-entering a score over the top works, but there was no way to send a match back to unplayed at all. | Improvement | New organizer-only 'Reset Score' button beside Submit Score in the score modal, shown only when the match already has a result — there is nothing to reset otherwise, and players cannot write the official record in any case. Confirms first, then reverses exactly the stats that one match awarded via reverseMatchStatsInto, which already handles walkovers, no-shows and doubles partner credits. Clears the result: status back to 'pending', winner and all six set values blanked, walkover and no_show flags cleared. Un-advances the winner — pulls them out of the next round's slot and restores 'Player Loading'. Uses the same bracket- and zone-normalised draw matching as advancement, because template match ids repeat across zone draws and an unnormalised lookup would clear a real player's slot in the OTHER zone. Never touches a next-round match that has already been played — that result belongs to whoever played it. DELIBERATELY does NOT reverse the RR group bonus: that is the organizer's own two-way switch, and silently flipping it here would take 5 points off every player in the group over an unrelated correction. Turn it off from the group card if the group should no longer count as finished. | An organizer can correct or undo one match without destroying the draw. Points, wins, losses, games and partner credits are all returned, the match becomes playable again, and the bracket slot the winner occupied is freed.
BUG-012 | Every player score submission was destroyed the moment it was actioned. Confirming a score deleted the submission, and a background sweep deleted any leftover submission once its match was complete. When both players submitted for the same match, the second copy — the only evidence of whether the two of them agreed — was silently swept away. Asked whether the two submissions for a match on 2026-08-15 carried the same score, the answer was unrecoverable: not one score_submission document survived anywhere in the database, and the notification trail stores only the pairing, with no score, submitter or set values. | Improvement | Submissions are now KEPT and stamped resolved ('confirmed' ¦ 'rejected' ¦ 'superseded') with resolved_at and resolved_by, instead of being deleted. 'superseded' is where the second player's copy lands — the case that previously vanished. The organizer's queue filters resolved submissions out at the snapshot, so the UI is unchanged and nothing new appears in it. The main matches subscription already filters category in ['singles','doubles'], so retained submissions stay invisible to the draw. No rules deploy needed — the creator catch-all in firestore.rules already permits updating any match doc carrying an event_id, which these do. | What each player submitted is on record and can be compared after the fact. NOT retroactive: submissions destroyed before this change cannot be recovered.
BUG-013 | The round-robin draw and its standings displayed things that were not true. (a) An entire generated Women's draw was invisible: it is stored merged (skill_group 'All'), but the merge inference keyed the merge by the RAW zone while the draw list keys it by the zone BUCKET id. The two never matched, so the merge was never applied, the draw stayed split into Challengers and Masters — neither of which owns a single match doc — and the page silently drew PREVIEW groups on top of a live draw holding 39 matches, 13 of them played. (b) The zone group header showed the raw bucket id 'downtown_midtown' instead of 'Downtown - Midtown', and the leaf row kept its zone suffix. (c) The standings table added +5 to every player the moment a group's last match completed — no longer true once the bonus became the organizer's manual switch, so players saw 5 points nobody had given them. | Improvement | (a) One canonical mergeZoneKey, used by the merge inference AND the header's merge toggles, so a match generated before zones existed resolves to the default bucket exactly like every other zone comparison in the file. The toggles now key off the visible draw's zone rather than activeZone, which starts undefined and could disagree with the page. (b) The merged-draw label now uses ' — ' as its separator. That separator is load-bearing, not decoration: DrawTabs recovers the zone name by splitting the label on it, and falls back to the raw bucket id when it finds nothing. The same split is how the leaf row strips its zone suffix, so one character fixed both halves. (c) The completion bonus was removed from computeGroupStandings. The table now shows only what was earned in the group's matches; the Group Bonus is the organizer's to award and is not displayed there. | The Women's groups and their played matches are reachable again — nothing was ever lost, only hidden. Zone names read properly in the draw tree. Displayed group points and actual league points agree again. Removing the automatic +5 also makes knockout seeding fairer: previously a winner from a group that happened to have finished carried a +5 head start over a winner from a group still in progress, so seeds were ordered partly by scheduling rather than results.
BUG-014 | An organizer editing one draw was thrown back to their own draw on every single edit. Editing anything in Challengers or Women's jumped the view to Men's Masters — the draw the organizer plays in — mid-edit, every time. | Improvement | The effect that lands a viewer on their own draw depended on userDraw by object IDENTITY. userDraw is memoized on `matches`, so any write anywhere in the event (a score, a seating, a group edit) handed it a brand-new object and re-ran the navigation. It now compares the destination's VALUE — event id, tab, division, skill group, zone — against a ref, and returns early when unchanged. The event id is part of the key so switching tournaments still re-lands the viewer. Verified there is exactly one programmatic writer of the active tab/skill/zone, so this covers every draw, not just the one reported. | The view stays where the organizer put it. It still lands them on their own draw on first load, and still moves them if their placement genuinely changes.
BUG-015 | On the Matches page: (a) an accepted challenge or friendly disappeared from the list, so the players could not record the score they had just played — reported live by a member. (b) Pressing the randomize dice on one row changed a DIFFERENT row. (c) The green tick and red cross for answering an incoming request were only visible after expanding the row, so the one thing needing a decision was the one thing you had to hunt for. | Improvement | (a) The list pins people you have a live match with, exempt from the ten-per-filter cap — but the pinned set was built only from `open` requests, so a person was un-pinned at the exact moment the match became scoreable. With four non-overlapping filters showing ten players each, they then vanished unless they happened to sit in the current filter's ten. The set now covers every non-terminal state: open, accepted and reported — pinned until confirmed/rejected (challenge) or confirmed/declined/disputed (rally), or cancelled. Verified symmetric: both the challenger and the challenged pin each other. (b) The rendered list is [pinned, ...pool] but the randomize overrides are keyed by POOL index, and each row passed its SCREEN index — so with N pinned rows the dice rewrote a row N positions further down. Each entry now carries its own pool slot and all slot logic uses that. Pinned rows carry slot -1 and show no dice at all, since rerolling away a person you have a live match with is exactly what pinning prevents. (c) Accept/Decline moved onto the collapsed row; the expanded cell now states the reason ('Challenged you' / 'Wants to rally') instead of duplicating the buttons. | A match you have agreed to stays on screen until it is recorded or cancelled, for both players. The dice affects the row you pressed it on. An incoming request can be answered without opening anything.
BUG-016 | Challenge and Friendly results were second-class citizens, stored in a different shape from tournament matches, and that caused two visible failures. (a) A CONFIRMED challenge or friendly appeared nowhere: it left the player's Upcoming list and never arrived in match history or completed matches — a played, confirmed, points-paying match with no trace on the History page, Profile's Recent Matches or the Home progress chart. Four confirmed challenges were already sitting in the database, invisible to the players who played them. (b) The score itself was stored as a single `score_line` string written games-first for whoever REPORTED it, so the other player's view of their own match was reversed — a 6-2, 7-5 win read as a 6-2, 7-5 loss. | Improvement | ROOT CAUSE: useUserMatches built its completed list only for tournament categories (singles/doubles). Challenges and rallies were handled solely for status 'accepted' to fill Upcoming; 'confirmed' fell through both branches and was dropped. Rather than teach every reader a second shape, challenge and rally results were NORMALISED to the tournament shape: winner_uid / winner_name plus absolute set_N_player_1 / set_N_player_2, and completed_at stamped on confirm. claimed_winner_uid/name and score_line are no longer written. Sets are stored ABSOLUTELY (player_1 first), which deletes the notion of a viewpoint entirely — the orientation bug cannot recur, and formatSetScores now serves every kind of result. Both submit paths orient once, at the point of writing, using a viewerIsP1 flag captured when the score modal opens. The tournament-to-challenge conversion path also had to reorder: the creator enters a score as the MATCH's player_1/player_2, but the challenge doc makes the PROPOSER its player_1. status stays on its own lifecycle ('confirmed'), because the deployed triggers, the finished-state checks and the row pinning all key off that exact value. DEPLOY SAFETY: four deployed Cloud Functions read the old names to pay points and notify. They now read winner_uid first and claimed_winner_uid as fallback, so points keep paying whichever order hosting and functions deploy in, and for documents in either shape. BACKFILL: 5 documents migrated via an Admin script, dry-run first and reviewed before writing. Validated by an independent check — in every row the recorded winner must end up with more games than the loser, and all 5 passed. The one row where the reporter was not player_1 was correctly flipped. Verified the write fired no triggers: the ladder points and notification triggers both return early when status is unchanged, and onMatchConnection requires status 'accepted'. Legacy fields are still present — removing them is a separate --delete-old pass that must run only AFTER functions and hosting are deployed. | A confirmed challenge or friendly appears in History, Profile and the progress chart with the correct score, winner and date for BOTH players. Every result in the app — tournament, challenge, friendly — now shares one storage shape, one formatter and one history mapping. The four already-confirmed challenges became visible without any client change.
BUG-017 | The Firestore export script silently dropped an entire dataset and wrote misleading empty files. `ranking_history` exported 0 rows every run — not because it was empty, but because all 313 weekly ranking snapshots live in ranking_history/{uid}/entries subcollections, and reading the top-level collection returns nothing. Separately, genuinely-empty collections (group_lessons, mailing_list) each wrote a 0-byte CSV, which beside real files reads as 'this data is gone' rather than 'nothing here yet' — the same disguise the legacy collections wore before they were removed from the list. | Improvement | The collection list now accepts { name, group } for data held in subcollections, and ranking_history is fetched with a collectionGroup('entries') query. Each exported row carries a _uid recovered from the entry's grandparent document, without which every ranking snapshot is anonymous. Empty collections are no longer written to disk. They stay configured — group_lessons and mailing_list are valid and will have rows later — but the run reports them as skipped instead of leaving a file that looks like data loss. The summary line now reports files written and collections skipped separately. VERIFIED: the export went from writing empty files and losing all 313 rankings to 3,270 documents across 18 files. Also confirmed while investigating: none of the 13 documented legacy collections (tournament_matches, rallies, ladder_challenges, score_submissions, task_progress, court_visits, court_attendance, court_reports, court_suggestions, redeemable, rewards, group_awards, zone_sweeps) holds a single document — nothing recreates them. | Exports contain the full ranking history instead of silently omitting it, and an empty file can no longer be mistaken for missing data. NOT FIXED, flagged only: 4 orphaned documents remain in the top-level rr_drafts collection from before drafts moved into the events/{id}/rr_drafts subcollection, and firestore.rules still declares a top-level /rr_drafts path that can never match the one the app uses.
BUG-018 | Players had no way to say how they want to be reached. Every opponent was offered Email, SMS and WhatsApp in a fixed order. A preference field (preferred_mode_of_contact) already existed, was defaulted at signup, was whitelisted in firestore.rules and was read by three code paths — but it had NO UI, NO WhatsApp option, and was ignored by ContactOpponentButton, the control that actually shows contact options. The three readers fed TournamentPlayer.contact / .preferredContact, which nothing rendered, and preferredContact was hardcoded to 'email' at four construction sites. | Improvement | preferred_mode_of_contact now holds a STRING ARRAY of 'email' ¦ 'text' ¦ 'whatsapp'. Empty or absent means no preference and every filled-in channel is offered — not 'email only' — so nothing regresses for existing members and no migration was needed. The key keeps its singular name so it stays inside ownerContactFields() and needs no rules deploy. Three always-visible 'Contact Method' switches on the profile card (SMS/Text, WhatsApp, Email), each beside its row's edit control. Not gated behind edit mode — they write a stored preference, not a draft. Independent of each other; each disabled when its channel has no detail saved, since a switch that silently does nothing is worse than one visibly unavailable. The cancel X is now red. An Email switch was added beyond the original ask: without it 'email AND WhatsApp' was inexpressible — you could only ever turn email off. contactChannels() is the single place the preference is applied, so every consumer (tournament, matches, profile, marketplace, services, player profile) inherits it. It only NARROWS: a channel with no detail is never offered, and a preference naming only channels since removed falls back to showing everything rather than nobody. DELETED the old path: TournamentPlayer.contact/.preferredContact, their four hardcoded construction sites, getContactValue, liveContact, and the preferred_mode_of_contact branch in the regroup script. | A member controls how they're contacted, WhatsApp is a first-class option, and there is one contact mechanism in the codebase instead of three.
BUG-019 | Three different mechanisms decided who ended up in a round-robin group, and two of them disagreed. Generation auto-formed groups; an in-browser effect then silently topped up any group under 5, IGNORING skill band and zone, but only while an organizer happened to have that draw open; and a nightly Admin script applied a different rule again (only groups of 3 or fewer, matching band required). Whichever ran first won, so a player's group depended on whether someone had a browser tab open. | Improvement | Both auto-placers deleted: the in-browser effect (~132 lines in useTournament.ts) and scripts/regroup-rr.js, plus its npm script and its now-stale Claude skill. The 'late joiner' concept is gone entirely. Generation still auto-forms the initial groups by the established hierarchy — zone, then skill, then court preference — and everyone else waits in the unplaced list until the organizer places them. Groups are capped at 5 (RR_GROUP_MAX). splitEvenly already never exceeds that when auto-forming; a new overGroupCap guard covers the manual paths (handleSeatParticipant, handleSaveGroupEdit, handleCreateRRGroup), which are now the only way anyone is seated. Deleting the script also removed one of the four hand-synced duplicate-logic pairs outright. | One placement path instead of three, with one rule. Nothing is seated without the organizer, and no group can exceed 5.
BUG-020 | The unplaced-players list was scoped to the event on screen, so a registrant in another tournament was invisible — an organizer could place a player into the wrong event without ever seeing they belonged to a different one. It also showed no zone, and the only zone value available (effectiveZone) defaults a player with no courts to Downtown-Midtown. | Improvement | The panel now spans EVERY tournament the organizer runs, and each row names the event the player actually joined. Seated-ness is tracked per event, since the same person can be placed in one tournament and not another. Each row shows the player's zone, and 'No zone' when they have selected no courts — read from their own preferences rather than effectiveZone, whose Downtown default exists for PLACEMENT only and would otherwise report a choice the player never made. rrUnplacedPlayers was deliberately NOT merged into this list: it is draw-scoped and feeds the Add Group picker, which must not offer another event's players. The distinction is now documented at both definitions. | An organizer can see everyone waiting for a place across all their tournaments, with the event and zone needed to place them correctly.
BUG-021 | Success and error banners were unreadable on the light theme. AlertMessage hardcoded text-green-300 / text-red-300 / text-amber-300 — pale palette colours that read fine on the dark surface and wash out to near-invisible on light theme's near-white one. This was app-wide: AlertMessage carries every banner. Behind it, 100 hardcoded status colours across 27 files had the same flaw, against only 10 uses of the theme-aware tokens that exist precisely to solve it — whose own comments in index.css describe this exact bug. | Improvement | AlertMessage moved to text-badge-win / text-badge-loss / text-badge. Swept all 103 hardcoded status colours across 26 files onto the tokens: green to badge-win, red to badge-loss, amber/yellow to badge, and orange/blue to clay (the brand accent used for required asterisks and actionable hints). Text only — tinted backgrounds and borders at 10-20% read fine in both themes. Also fixed the nine remaining foreground violations of the documented two-tier rule (text-fg/50, /40, /30 in ServicesElements, MatchCard, RRGroupCard) — raised to /70, with opacity-70 where 'muted' was the intent. One filled chip used 'bg-orange-500 text-fg', which puts dark green on orange in light theme; changed to bg-clay text-white, matching the documented rule for filled buttons. | Banners are legible in both themes, and status colour is expressed once, in tokens that flip with the theme, rather than 100 hardcoded classes that don't.
BUG-022 | GEMINI_API_KEY was compiled into the JavaScript every visitor downloads. vite.config.ts inlined it via `define:`, which performs a literal text substitution at build time — and nothing in src/ ever read it. A real credential published to the public for no purpose. | Improvement | Deleted the entire `define:` block and the now-unused loadEnv import. The file carries a short note that secrets belong in a Cloud Function, pointing at CLAUDE.md. NOTE: the key itself should still be revoked and reissued — it has been in public bundles and must be assumed compromised. That is outside the codebase. | No secret is compiled into the client bundle, and there is no `define:` block left for one to be added to casually.
BUG-023 | RR drafts had not saved for months, silently. The client writes them to the subcollection events/{eventId}/rr_drafts/{drawKey}, but firestore.rules declared a TOP-LEVEL /rr_drafts/{id} — and rules do not cascade into subcollections, so every draft read and write was denied by default. The onSnapshot error path sets the draft to null, so it failed with no error surfaced. Confirmed live: zero nested drafts existed anywhere. | Improvement | Moved the rule to the nested path events/{eventId}/rr_drafts/{drawKey}, matching where the client actually writes. Needs a rules deploy. The four surviving top-level documents were MIGRATED to the nested path rather than deleted as originally planned — inspection showed they held real state, including 11 withdrawal records in one draft, which are what stop removed players being re-seated. Deleting them would have destroyed the only draft state left. The script copied, verified the copy, then deleted the original; top-level rr_drafts is now empty. | Draft group arrangements and withdrawal lists save again, and the surviving state was preserved rather than discarded.
BUG-024 | A player could not request a zone change at all. handleRequestZoneChange writes req_zone_change and new_zone, but the rules' player-write whitelist listed only the legacy zone_change_requested pair — so hasOnly() rejected the whole update for any non-creator. Separately, the client was writing BOTH the new and legacy flags because the deployed Cloud Function triggered on the old name, and handleClearZoneChangeRequest cleared only the legacy flag, so clearing a request did nothing to the live one. | Improvement | firestore.rules: added req_zone_change and new_zone to the participant self-write whitelist. The legacy pair is retained for now so the currently-deployed client keeps working, and is marked for removal after the next hosting deploy. The Cloud Function now triggers on req_zone_change, reading the legacy name as a fallback so in-flight requests from an older client still notify. The client no longer writes the legacy flags, and clearing a request now clears both. Needs a rules deploy AND a functions deploy. | Zone change requests work for players at all, and there is one flag driving them instead of two that disagreed about which was authoritative.
BUG-025 | The points a player was PAID and the points they were SHOWN came from two separate implementations of the same rules — computeMatchPoints (writes stats.leaguePoints26) and computeGroupStandings (draws the group table) — and they had already drifted: the table kept adding a +5 completion bonus long after the payout became the organizer's manual switch, so players were shown 5 points nobody had given them. | Improvement | Merged into one function, matchAward in utils.ts, read by both the writer (updateMatchWithSubmission, reverseMatchStatsInto) and the display (computeGroupStandings). NO_SHOW_POINTS moved there too. The rules now live in exactly one place: an RR group win pays 3 and the loss 1 whether or not it was a walkover; a knockout pays by how far you got, banked when you go out, and its winner only scores by taking the final; a no show has no winner and pays both players 1. computeGroupStandings keeps only what is genuinely display-side — wins, losses, games and the ordering. | The group table can no longer disagree with the points actually paid, because there is no second implementation left to drift.
BUG-026 | The --delete-old pass of the result-shape migration could never run. It shared its candidate filter with the backfill pass — `!winner_uid && hasLegacy` — but after the backfill every document HAS winner_uid, so the filter excluded all of them and the pass matched nothing. | Improvement | The two passes now select different documents, as they always should have: backfill takes rows not yet migrated (no winner_uid, still legacy); --delete-old takes rows already migrated that still carry legacy fields (winner_uid present AND legacy present). Dry-run verified: it now selects all 5 documents and lists exactly which fields it would keep and which it would drop. NOT YET RUN. Precondition unchanged — functions and hosting must both be deployed first, because the currently-deployed functions still read claimed_winner_uid. | The legacy fields can actually be removed once the deploy lands, instead of the cleanup pass silently doing nothing.